## Instructions
Workbook Instructions
Cover Tab
Field Letter | Instructions
A | Enter the Customer Name (Text Field)
B | Enter the Project Name (Text Field)
C | Enter the Project ID (Text Field)
D | Enter the Project Manager Name (Text Field)
E | Used To document version control of the workbook (Date Field for cells B18:B36 and Text Field for remainder of table)
Requirements Traceability Tab
Field Letter | Instructions
F | ID column: Enter unique requirements identifier number (see note for instructions) Business Requirements or User Story column: Enter business requirement or customer outcome expected to be addressed by the requirement Requirements Type column: Enter specific functional or technical requirements expected to support the business requirement (see note for instructions) Technology Area column: The technology area / system qualities that the requirement affects Requirement Source column: Identify where the requirement originated from Requirement Source Date column: Identify when the requirement was identified Priority (MoSCoW) column: classify each requirement as Must Have, Should Have, Could Have and Won't Have Priority column: Identify requirement priority using MoSCoW critieria (drop down field)(see note for instructions) Requirement Raised By column: VMware or Customer Test Scenario Description column: Briefly describe the test scenario to valudate the requirement
G | Validated By Column: Enter the person that performed the validation Validation Date Column: Enter the date the validation occurred Validation Status Column: Enter the Validation Status (drop down field) Defect ID Column: If Validation was not successful, list a unique identifier as a defect ID
Other Tabs
Field Letter | Instructions
N/A | Instructions on how to use these tabs should be self explanatory

## Cover
Global Delivery Excellence
Project Requirements Traceability Matrix and RAID Cover
Project Background:
| Customer Name: | RFG (Redwood Financial Group) |  |  | Instructions: Enter information sequentially into the letttered green highlighed cells on each tab within this workbook. Note that overwriting or erasing non-green highlighted cells may erase formulas and destabilize the built-in automation features.
| Project Name: | BEAT (Business Enabled Application Transformation) 2022
| Project ID: | RFG2022
| Project Manager: | Team 3
Note 1: All date formats are MM/DD/YYYY
Project Version Control:
| Date | Version | Comments | Editor
| 2019-06-10 | 0.1 | Early Draft | Marshall Massengill
| 2019-06-19 | 0.2 | Final version | Team 3
Note on C6: Insert Customer's Name Here
Note on C8: Insert Project Name Here
Note on C10: Insert ChangePoint Project ID Here
Note on C12: Insert Name of VMware Project Manager Here
A
B
C
D
E

## Requirements Traceability
Global Delivery Excellence
Project Requirements Traceability Matrix
| Project ID: RFG2022 |  |  |  |  | Note: Use separate rows to identify multiple function requirements for a single business requirement or user story
Customer Name: RFG (Redwood Financial Group)
Project Manager: Team 3
| Definition | [8 empty] | Validation
| Req ID | Business Requirement or User Story | Requirement Type: Functional or Technical | Technology Area | Requirement Source | Requirments Source Date | Priority (MoSCoW) | Requirement Raised by: VMware or Customer | Test Scenario Description | Validated By | Validation Date | Validation Status | Defect Identifier
| SR01 | Ability to utilize public networks for access to desktop image | Functional: Provide desktop image access over public networks to qualified users | Security | SOW Section 5.3 | 2018-10-15 | Must Have | Customer / SOW Requirement | Complete functional and user acceptance testing
| SR01 | System will be available in four regions | Functional: Systems in NA, EMEA, LATAM, APAC | Architecture | Introduction | 2019-06-10 | Must Have | Customer | Functional testing |  |  |  |  | Must Have | Passed | Architecture
| SR02 | System implemented in phases | Functional: To enable customer to experience early success | Architecture | Introduction | 2019-06-10 | Must Have | Customer | Functional testing |  |  |  |  | Should Have | Failed | Functionality
| SR03 | Reduce M&A time to less than 12 months | Functional: reduce time for M&A | Architecture | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing |  |  |  |  | Could Have | Blocked | User Access
| SR04 | Reduce operationalizing new regional and local retail banking branches | Functional: Reduce time to four to six months | Architecture | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing |  |  |  |  | Won't Have | Retest | Security
| SR05 | Enable BDA for each region | Functional: customer wants to leverage BDA for consumer analytics BI Project | Architecture | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing | [6 empty] | Capacity Monitoring
| SR06 | Enable IoT for each region | Functional: customer wants to leverage IoT to deliver customer services based on geo-spatial coordinates | Architecture | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing | [6 empty] | Provisioning
| SR07 | Secure Business against cyber attacks | Functional: Securing business against cyber threats and DDoS attacks | Security | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing | [6 empty] | Disaster Recovery
| SR08 | Provide agreed SLA uptime | Functional: guaranteeing operational uptime | Disaster Recovery | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing | [6 empty] | Operations
| SR09 | Leverage cross-cloud and hybrid cloud technologies | Functional: to support security and scalability for seasonal demand | Provisioning | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing | [6 empty] | Server Sizing
| SR10 | DR to public cloud | Functional: Leverage public cloud for DR scenario | Disaster Recovery | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing | [6 empty] | RAD Applications
| SR11 | Leverage automation to decrease application deployment time | Functional: accelerate time to market for new products and services | Provisioning | Leadership Objectives - CEO | 2019-06-10 | Must Have | Customer | Functional testing | [6 empty] | Service Level
| SR12 | Enable metering, monitoring, and chargeback | Functional: Enable reusable cloud services | Operations | Leadership Objectives - CFO | 2019-06-10 | Must Have | Customer | Functional testing | [6 empty] | Other
| SR13 | Provide accurate pricing for service catalog | Functional: price individual items in IT service catalog | Operations | Leadership Objectives - CFO | 2019-06-10 | Must Have | Customer | Functional testing
| SR14 | Pass regional and global regulatory compliance audits | Functional: Data in motion and at rest needs to be secured | Operations | SVP Compliance and Governance | 2019-06-10 | Must Have | Customer | Functional testing
| SR15 | Define clear separation of duties | Functional: team of no more than 5 people per region will be allowed production access | Operations | SVP Compliance and Governance | 2019-06-10 | Must Have | Customer | Functional testing
| SR16 | Enforce environment separation | Functional: disallow anyone with access to the code to have access to the production environments | Security | SVP Compliance and Governance | 2019-06-10 | Must Have | Customer | Functional testing
| SR17 | Improve network security monitoring | Functional: Leverage tooling to provide network security monitoring | Security | SVP Compliance and Governance | 2019-06-10 | Must Have | Customer | Functional testing
| SR18 | Standardize development environments | Functional: introduce centralized governance model | Provisioning | SVP-Business Innovations | 2019-06-10 | Must Have | Customer | Functional testing
| SR19 | Enable developers to build microservice based applications | Functional: Provide infrastructure for microservice management to developers | Provisioning | SVP-Business Innovations | 2019-06-10 | Must Have | Customer | Functional testing
| SR20 | Simplify lifecycle management | Functional: Improve change management | Operations | SVP Infrastructure | 2019-06-10 | Must Have | Customer | Functional testing
| SR21 | Limit outage fault zones | Functional: increase success rate of infrastructure updates | Operations | SVP Infrastructure | 2019-06-10 | Must Have | Customer | Functional testing
| SR22 | Offer self-service cloud based delivery | Functional: self-service for provisioning that includes firewalls, VPNs, and branch office connectivity | Operations | SVP Infrastructure | 2019-06-10 | Must Have | Customer | Functional testing
| SR23 | Improve BYOD security and device management | Functional: improved reporting, management, and security of end user devices | Security | SVP-EUC | 2019-06-10 | Must Have | Customer | Functional testing
| SR30 | Business innovation & agility | Functional: key imperative to realize BEAT2020 vision | Other | Leadership Objectives - CEO | 2019-06-19 | Must Have | Customer | Functional testing
| SR31 | Digital trasformation | Functional: Flexible information availability | User Access | Leadership Objectives - CEO | 2019-06-19 | Should Have | Customer | Functional testing
| SR32 | Business continuity plan | Functional: guaranting operational uptime | Architecture | Leadership Objectives - CEO | 2019-06-19 | Must Have | Customer | Functional testing
| SR33 | ITaaS | Functional: Recusable cloud services such as meter, monitoring and chargeback | Operations | Leadership Objectives - CFO | 2019-06-19 | Should Have | Customer | Functional testing
| SR34 | significant and gradual decrease in CAPEX and OPEX | Functional | Service Level | Leadership Objectives - CEO | 2019-06-19 | Should Have | Customer | Functional testing
F
G
Note on B9: Each requirement requires a unique ID. This ID needs to map to the design document and design decision. If there is a central equirements document it will contain requirements from each workstream. Therefore it's important to have a unique identifier for each workstream. Identifier examples are as follows; <Customer>-<Phase>-Workstream>-<Requirement Classification>-<Unique Number> Unique Number will be assigned by PM Customer 2 Letter Identifier Project Phase If applicable Workstream (ie, vROPs, SRM, vRA, SDDC, EUC) or may relate to a workstream defined in the statement of work for larger projects Requirement classification Business Drivers = BD Business Requirements = BR Functional Requirements General = GR Availability = AR Manageability = MR Performance = PR Recoverability = RR Security = SR Operational = OR Technical Requirements Infrastructure = ITR Network = NTR Storage = STR Backup = BTR Orchestration = OTR Service Lifecycle = STR Integration = ITR
Note on C9: The business requirement / need. This can come direct from ITVM business need examples or from the customer
Note on F9: Functional: What will the solution do, and what information will it provide ? What qualities and services will it provide, and for which users ? Technical: How will the solution be structured, constructed, constrained, Managed? Requirements for applications, data, interfaces, infrastructure
Note on I9: Technology Area that the requirement relates to. Use drop down selections as appropriate.
Note on L9: Name of person or document name (with version, author, location) where requirement was noted. If during a workshop, state workshop name.
Note on O9: Date requirement was identified. If in SOW, list SOW execution date
Note on Q9: Requirements prioritization model that is used by VMware to manage the importance and criticality of requirements to the success of a project. Must Have: This type of requirement must be provided or project will fail Should Have: Should be delivered unless time / money / resources are constrained Could Have: Nice to haves that could be implemented depending on other constraints Won't Have: May be desired but constraints will not allow the implementation
Note on S9: Name / Role of the person who has identified the requirement. Use specific names as opposed to more generic naming conventions. Use the Project RACI to identify correct role definitions.
Note on V9: Describe the test process by which the requriement will be validated

## Technical Risk Register
Global Delivery Excellence
Technical Risk Register
Project ID: RFG2022
Customer Name: RFG (Redwood Financial Group)
Project Manager: Team 3
| ID# | Risk Description (Include Risk Trigger) | Impact Description if Triggered | Risk Category | Risk Probability Level | Risk Impact Level | Risk Score | Originator | Owner | Date Identified | Risk Response Strategy | Date Triggered or Resolved | Transfer to Issue or Action ID# | Risk Management Updates (Include Dates)
| R-1 | Business operation transformation | ignoring technology advancements in day-to-day business operations can impede business agility. | Cost | Somewhat Likely (25-50%) | High Impact | High Risk | CEO | Business Ops | 2019-06-19 | Accept |  |  |  | 2 | 3
| R-2 | Fragile Infrastructure | Unsuccessful change management and business outage | Cost | Likely (50-75%) | High Impact | High Risk | SVP-Infra |  | 2019-06-19 | Mitigate |  |  |  | 3 | 3
| R-3 | Servers are infected with "Ransom-ware" virus | This incident follows a data breach last year involving a situation where hackers appropriated client financial data files | Cost | Likely (50-75%) | High Impact | High Risk | SVP-EUC |  | 2019-06-19 | Mitigate |  |  |  | 3 | 3
| R-4 | Access management are outdated | Users should track multiple system password, many admin user have admin previlege | Quality | Likely (50-75%) |  |  | SVP-EUC |  | 2019-06-19 | Mitigate |  |  |  | 3 | 0
| R-5 | Win7 EOL support |  | Resources | Very Likely (>75%) | Moderate Impact | High Risk | SVP-EUC |  | 2019-06-19 | Accept |  |  |  | 4 | 2
| R-6 | Mac OS X machines are nearly invisible on our system – we can’t track, scan or audit them | our security scanning software is Windows-based | Resources | Likely (50-75%) |  |  | SVP-EUC |  | 2019-06-19 | Mitigate |  |  |  | 3 | 0
| R-7 | [13 empty] | 0 | 0
| R-8 | [13 empty] | 0 | 0
| R-9 | [13 empty] | 0 | 0
| R-10 | [13 empty] | 0 | 0
| R-11 | [13 empty] | 0 | 0
| R-12 | [13 empty] | 0 | 0
| R-13 | [13 empty] | 0 | 0
| R-14 | [13 empty] | 0 | 0
| R-15 | [13 empty] | 0 | 0
| R-16 | [13 empty] | 0 | 0
| R-17 | [13 empty] | 0 | 0
| R-18 | [13 empty] | 0 | 0
| R-19 | [13 empty] | 0 | 0
| R-20 | [13 empty] | 0 | 0
| R-21 | [13 empty] | 0 | 0
| R-22 | [13 empty] | 0 | 0
| R-23 | [13 empty] | 0 | 0
| R-24 | [13 empty] | 0 | 0
| R-25 | [13 empty] | 0 | 0
| R-26 | [13 empty] | 0 | 0
| R-27 | [13 empty] | 0 | 0
| R-28 | [13 empty] | 0 | 0
| R-29 | [13 empty] | 0 | 0
| R-30 | [13 empty] | 0 | 0
| R-31 | [13 empty] | 0 | 0
| R-32 | [13 empty] | 0 | 0
| R-33 | [13 empty] | 0 | 0
| R-34 | [13 empty] | 0 | 0
| R-35 | [13 empty] | 0 | 0
| R-36 | [13 empty] | 0 | 0
| R-37 | [13 empty] | 0 | 0
| R-38 | [13 empty] | 0 | 0
| R-39 | [13 empty] | 0 | 0
| R-40 | [13 empty] | 0 | 0
| R-41 | [13 empty] | 0 | 0
| R-42 | [13 empty] | 0 | 0
| R-43 | [13 empty] | 0 | 0
| R-44 | [13 empty] | 0 | 0
| R-45 | [13 empty] | 0 | 0
| R-46 | [13 empty] | 0 | 0
| R-47 | [13 empty] | 0 | 0
| R-48 | [13 empty] | 0 | 0
| R-49 | [13 empty] | 0 | 0
| R-50 | [13 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0 | Cost | Unlikely (<25%) | Little Impact
[15 empty] | 0 | 0 | Quality | Somewhat Likely (25-50%) | Moderate Impact
[15 empty] | 0 | 0 | Schedule | Likely (50-75%) | High Impact
[15 empty] | 0 | 0 | Scope | Very Likely (>75%) | Critical Impact
[15 empty] | 0 | 0 | Resources
[15 empty] | 0 | 0
[15 empty] | 0 | 0 |  | Avoid
[15 empty] | 0 | 0 |  | Transfer
[15 empty] | 0 | 0 |  | Mitigate
[15 empty] | 0 | 0 |  | Accept

## Technical Issue Register
Global Delivery Excellence
Issue Register
Project ID: RFG2022
Customer Name: RFG (Redwood Financial Group)
Project Manager: Team 3
| ID# | Issue Description | Related Risk ID | Status (Active/ Resolved) | Priority (L,M,H) | Originator | Owner | Date Identified | Planned Resolution Date | Aging Forecast Date | Actual Resolution Date | Status (Include Dates)
| I-1 | 90% time spent on IT operation, less time(10%) on Innovation |  | Active | Medium | CFO | IT | 2019-06-19
| I-2 | Capacity Management |  | Active | Medium
| I-3 | Internal and External data is stored in external cloud |  | Active | Low
| I-4 | Firewall set to Any-Any |  | Active | High
| I-5 | Leveraging Multiple tools to manage and secure environment |  | Active | Medium
I-6
I-7
I-8
I-9
I-10
I-11
I-12
I-13
I-14
I-15
I-16
I-17
I-18
I-19
I-20
I-21
I-22
I-23
I-24
I-25
I-26
I-27
I-28
I-29
I-30
I-31
I-32
I-33
I-34
I-35
I-36
I-37
I-38
I-39
I-40
I-41
I-42
I-43
I-44
I-45
I-46
I-47
I-48
I-49
I-50
[13 empty] | Active | Low
[13 empty] | Resolved | Medium
High

## Technical CDEA Register
Global Delivery Excellence
Constraint, Dependency, Exclusion, Assumption Register
Project ID: RFG2022
Customer Name: RFG (Redwood Financial Group)
Project Manager: Team 3
| ID# | Constraint, Dependency, Exclusion, Assumption Type | Description | Originator | Date Identified | Status | Date Validated | Validated By | Notes
| CDEA-1 | Assumption | No implementation of BETA phases | Vmware | 2019-06-10 | Identified
| CDEA-2 | Assumption | No mention of total end users | Vmware | 2019-06-10 | Identified
| CDEA-3 | Assumption | No year value for completing exsiting M&As | Vmware | 2019-06-10 | Identified
| CDEA-4 | Assumption | Don't know BDA for each region | Vmware | 2019-06-10 | Identified
| CDEA-5 | Assumption | No Existing IoT Solution | Vmware | 2019-06-10 | Identified
| CDEA-6 | Assumption | EUC digital transformation to be used by internal users and partners | Vmware | 2019-06-10 | Identified
| CDEA-7 | Assumption | no existing solution for data security | Vmware | 2019-06-10 | Identified
| CDEA-8 | Dependency | BEAT2022 success depemds on business innovation | CEO | 2019-06-19 | Identified
| CDEA-9 | Constraint | Oracle infrastructure data is strcutrured format | CFO | 2019-06-19 | Identified
| CDEA-10 | Constraint | Users using BYOD devices | SVP-EUC | 2019-06-19 | Identified
| CDEA-11 | Constraint | We are seriously considering migration to Win10 but for the certain applications across various Geos we would be compelled to continue using Win7 | SVP-EUC | 2019-06-19 | Identified
| CDEA-12 | Assumption
CDEA-13
CDEA-14
CDEA-15
CDEA-16
CDEA-17
CDEA-18
CDEA-19
CDEA-20
CDEA-21
CDEA-22
CDEA-23
CDEA-24
CDEA-25
CDEA-26
CDEA-27
CDEA-28
CDEA-29
CDEA-30
CDEA-31
CDEA-32
CDEA-33
CDEA-34
CDEA-35
CDEA-36
CDEA-37
CDEA-38
CDEA-39
CDEA-40
CDEA-41
CDEA-42
CDEA-43
CDEA-44
CDEA-45
CDEA-46
CDEA-47
CDEA-48
CDEA-49
CDEA-50
Constraint
Dependency
Exclusion
Assumption
Identified
Baselined
Completed
Late
No Longer Relevant